## User Stories
v 0.1
Misc
Progress Bar on top

## collections
quote
| clientAddress | text area text
| units | mm or inch, TEXT_CONST
| type | TEXT_CONST
| numberOfLeafs | 1 or 2
| size | height, width
| glassSize | height, width
| rubberSealing | size (number)
| lockType | TEXT_CONST
| doorClosers | number
| quantity | number

## Development Time Reqd
Module | No of Hrs | Comments
Animation Tut | 1 |  | Total 11 Skide
App Master State | 1
Slide-1 UI and State/Props | 1
Slide 2 | 0.5
Slide 3 | 0.5
Slide 4 | 0.5
Slide 5 | 0.5
Slide 6 | 0.5
Slide 7 | 0.5
Slide 8 | 0.5
Slide 9 | 0.5
Slide 10 | 0.5
Slide 11 | 0.5
Calculating cost for each door property, .75 x 9 | 6.75
Display Final | 0.5
Total | 15.25
x 3 as per Dev Mastery | 45.75 | 1 month on 2 hrs per day Start Date: 03-10-2017